## Risk Chart - No Decompression
Design Option | Duration | Direct Cost | Criticality Risk | Activity Risk
Simulators | 7.1333 | 34.8067 | 0.80556 | 0.75661
Infra + Clients Front End | 7.8333 | 30.3733 | 0.77174 | 0.80978
TopDev2+TopDev1 | 8.5333 | 26.5933 | 0.78571 | 0.80272
TopDev2 | 9.4667 | 24.2133 | 0.70238 | 0.77489
Normal | 9.9333 | 21.8333 | 0.72619 | 0.79487
Sub-Critical | 13.4333 | 20.9 | 0.78571 | 0.78571
Subcritical
Simulators
Infra+Clients
Front-End
TopDev2+
TopDev1
TopDev2
Normal

## Risk Chart
Design Option | Duration | Criticality Risk | Activity Risk | Raw Activity Risk | Fibonacci Risk
Simulators | 7.1333 | 0.80556 | 0.75661 | 0.75661 | 0.78986
Infra + Clients Front End | 7.8333 | 0.77174 | 0.80978 | 0.80978 | 0.72495
TopDev2+TopDev1 | 8.5333 | 0.78571 | 0.80272 | 0.80272 | 0.74372
TopDev2 | 9.4667 | 0.70238 | 0.77489 | 0.77489 | 0.65972
Normal | 9.9333 | 0.72619 | 0.79487 | 0.79487 | 0.6822
D4 | 10.4 | 0.45238 | 0.53931 | 0.69524 | 0.36971
D3 | 10.8667 | 0.42857 | 0.44654 | 0.61905 | 0.35582
D2 | 12.0333 | 0.28571 | 0.3261 | 0.48918 | 0.27245
D1 | 13.4333 | 0.28571 | 0.26701 | 0.39456 | 0.27245
0.01140421x3 - 0.36328955x2 + 3.66630481x - 11.07269795
0.01188690x3 - 0.37185214x2 + 3.68978289x - 10.99313755
D1
D2
D3
D4
Simulators
Infra+Clients
Front End
TopDev1+
TopDev2
TopDev2
Normal

## Risk and Direct Cost
Design Option | Duration | Direct Cost
Simulators | 7.1333 | 34.8067
Infra + Clients Front End | 7.8333 | 30.3733
TopDev2+TopDev1 | 8.5333 | 26.5933
TopDev2 | 9.4667 | 24.2133
Normal | 9.9333 | 21.8333
D1 | 13.4333 | 28.8333
D1
D2
D3
D4
Simulators
Infra+Clients
Front End
Normal
TopDev1+
TopDev2
TopDev2

## Time Cost
Design Option | Duration | Direct Cost | Indirect Cost | Total Cost
Simulators | 7.1333 | 34.8 | 28.7333 | 63.5333
Infra + Clients Front End | 7.8333 | 30.3733 | 32.2333 | 62.6067
TopDev2+TopDev1 | 8.5333 | 26.5933 | 32.7 | 59.2933
TopDev2 | 9.4667 | 24.2133 | 36.9 | 61.1133
Normal | 9.9333 | 21.8333 | 39.2333 | 61.0667
D1 | 13.4333 | 28.8333 | 51.1372 | 79.9705

## Time Cost Model
Coefficients |  | Direct Cost | Incirect cost | Total Cost
a |  | 0.98971 | 3.5393 | 0.98971 |  |  |  | Total cost at D3 | 10.8667 | 63.8434
b |  | -21.3173 | 3.5932 | -17.778
c |  | 136.5684 |  | 140.1616
Duration | Total Cost | Direct Cost | Indirect Cost
6 | 69.1232 | 44.2945 | 24.8287
6.1 | 68.5429 | 43.3603 | 25.1826
6.2 | 67.9825 | 42.4459 | 25.5366
6.3 | 67.4418 | 41.5513 | 25.8905
6.4 | 66.9209 | 40.6765 | 26.2444
6.5 | 66.4199 | 39.8215 | 26.5983
6.6 | 65.9386 | 38.9863 | 26.9523
6.7 | 65.4771 | 38.1709 | 27.3062
6.8 | 65.0354 | 37.3753 | 27.6601
6.9 | 64.6135 | 36.5995 | 28.014
7 | 64.2114 | 35.8434 | 28.368
7.1 | 63.8291 | 35.1072 | 28.7219
7.2 | 63.4666 | 34.3908 | 29.0758
7.3 | 63.1239 | 33.6941 | 29.4298
7.4 | 62.8009 | 33.0173 | 29.7837
7.5 | 62.4978 | 32.3602 | 30.1376
7.6 | 62.2145 | 31.7229 | 30.4915
7.7 | 61.9509 | 31.1055 | 30.8455
7.8 | 61.7072 | 30.5078 | 31.1994
7.9 | 61.4832 | 29.9299 | 31.5533
8 | 61.2791 | 29.3718 | 31.9072
8.1 | 61.0947 | 28.8335 | 32.2612
8.2 | 60.9301 | 28.315 | 32.6151
8.3 | 60.7854 | 27.8163 | 32.969
8.4 | 60.6604 | 27.3374 | 33.3229
8.5 | 60.5552 | 26.8783 | 33.6769
8.6 | 60.4698 | 26.439 | 34.0308
8.7 | 60.4042 | 26.0195 | 34.3847
8.8 | 60.3584 | 25.6197 | 34.7386
8.9 | 60.3324 | 25.2398 | 35.0926
9 | 60.3261 | 24.8797 | 35.4465 |  | Normal | 9.9333 | 80
9.1 | 60.3397 | 24.5393 | 35.8004 |  | Min Total | 8.9814 | 80
9.2 | 60.3731 | 24.2188 | 36.1543
9.3 | 60.4263 | 23.918 | 36.5083
9.4 | 60.4992 | 23.637 | 36.8622
9.5 | 60.592 | 23.3759 | 37.2161 |  | Min direct | 10.7694 | 21.781
9.6 | 60.7045 | 23.1345 | 37.57
9.7 | 60.8369 | 22.9129 | 37.924
9.8 | 60.989 | 22.7111 | 38.2779
9.9 | 61.1609 | 22.5291 | 38.6318
10 | 61.3526 | 22.3669 | 38.9857
10.1 | 61.5642 | 22.2245 | 39.3397
10.2 | 61.7955 | 22.1019 | 39.6936
10.3 | 62.0466 | 21.9991 | 40.0475
10.4 | 62.3175 | 21.916 | 40.4014
10.5 | 62.6082 | 21.8528 | 40.7554
10.6 | 62.9187 | 21.8094 | 41.1093
10.7 | 63.249 | 21.7857 | 41.4632
10.8 | 63.599 | 21.7819 | 41.8171
10.9 | 63.9689 | 21.7978 | 42.1711
11 | 64.3586 | 21.8336 | 42.525
11.1 | 64.768 | 21.8891 | 42.8789
11.2 | 65.1973 | 21.9644 | 43.2329
11.3 | 65.6463 | 22.0596 | 43.5868
11.4 | 66.1152 | 22.1745 | 43.9407
11.5 | 66.6038 | 22.3092 | 44.2946
11.6 | 67.1122 | 22.4637 | 44.6486
11.7 | 67.6405 | 22.638 | 45.0025
11.8 | 68.1885 | 22.8321 | 45.3564
11.9 | 68.7563 | 23.046 | 45.7103
12 | 69.3439 | 23.2797 | 46.0643
12.1 | 69.9513 | 23.5331 | 46.4182
12.2 | 70.5785 | 23.8064 | 46.7721
12.3 | 71.2255 | 24.0995 | 47.126
12.4 | 71.8923 | 24.4123 | 47.48
12.5 | 72.5789 | 24.745 | 47.8339
12.6 | 73.2852 | 25.0974 | 48.1878
12.7 | 74.0114 | 25.4697 | 48.5417
12.8 | 74.7574 | 25.8617 | 48.8957
12.9 | 75.5231 | 26.2735 | 49.2496
13 | 76.3087 | 26.7052 | 49.6035
13.1 | 77.114 | 27.1566 | 49.9574
13.2 | 77.9392 | 27.6278 | 50.3114
13.3 | 78.7841 | 28.1188 | 50.6653
13.4 | 79.6488 | 28.6296 | 51.0192
13.5 | 80.5333 | 29.1602 | 51.3731
13.6 | 81.4376 | 29.7106 | 51.7271
13.7 | 82.3618 | 30.2808 | 52.081
13.8 | 83.3057 | 30.8707 | 52.4349
13.9 | 84.2694 | 31.4805 | 52.7888
14 | 85.2529 | 32.1101 | 53.1428
14.1 | 86.2561 | 32.7594 | 53.4967
14.2 | 87.2792 | 33.4286 | 53.8506
14.3 | 88.3221 | 34.1175 | 54.2045
14.4 | 89.3848 | 34.8263 | 54.5585
14.5 | 90.4672 | 35.5548 | 54.9124
14.6 | 91.5695 | 36.3032 | 55.2663
14.7 | 92.6915 | 37.0713 | 55.6202
14.8 | 93.8334 | 37.8592 | 55.9742
14.9 | 94.995 | 38.6669 | 56.3281
15 | 96.1765 | 39.4944 | 56.682
Normal
Minimum
Total Cost
Minimum
Direct Cost

## Risk Cost Models
Coefficients | Direct Cost | Activity Risk
a | 0.98971 | 0.011404
b | -21.3173 | -0.36329
c | 136.5684 | 3.6663
d |  | -11.0727
Duration | Direct Cost | Activity Risk
6 | 44.2945 | 0.31002
6.1 | 43.3603 | 0.3623
6.2 | 42.4459 | 0.41148
6.3 | 41.5513 | 0.45765
6.4 | 40.6765 | 0.50086
6.5 | 39.8215 | 0.54118
6.6 | 38.9863 | 0.57869
6.7 | 38.1709 | 0.61344
6.8 | 37.3753 | 0.64551
6.9 | 36.5995 | 0.67498
7 | 35.8434 | 0.70189
7.1 | 35.1072 | 0.72633
7.2 | 34.3908 | 0.74836
7.3 | 33.6941 | 0.76806
7.4 | 33.0173 | 0.78548
7.5 | 32.3602 | 0.8007
7.6 | 31.7229 | 0.81379
7.7 | 31.1055 | 0.82481
7.8 | 30.5078 | 0.83383
7.9 | 29.9299 | 0.84093
8 | 29.3718 | 0.84616
8.1 | 28.8335 | 0.84961
8.2 | 28.315 | 0.85133
8.3 | 27.8163 | 0.85139
8.4 | 27.3374 | 0.84987
8.5 | 26.8783 | 0.84683
8.6 | 26.439 | 0.84234
8.7 | 26.0195 | 0.83647
8.8 | 25.6197 | 0.82929
8.9 | 25.2398 | 0.82086
9 | 24.8797 | 0.81126
9.1 | 24.5393 | 0.80055
9.2 | 24.2188 | 0.7888
9.3 | 23.918 | 0.77608
9.4 | 23.637 | 0.76246
9.5 | 23.3759 | 0.748
9.6 | 23.1345 | 0.73278
9.7 | 22.9129 | 0.71686
9.8 | 22.7111 | 0.70031
9.9 | 22.5291 | 0.6832
10 | 22.3669 | 0.66561
10.1 | 22.2245 | 0.64758
10.2 | 22.1019 | 0.62921
10.3 | 21.9991 | 0.61054
10.4 | 21.916 | 0.59166
10.5 | 21.8528 | 0.57263
10.6 | 21.8094 | 0.55352
10.7 | 21.7857 | 0.53439
10.8 | 21.7819 | 0.51532
10.9 | 21.7978 | 0.49638
11 | 21.8336 | 0.47762
11.1 | 21.8891 | 0.45913
11.2 | 21.9644 | 0.44097
11.3 | 22.0596 | 0.4232
11.4 | 22.1745 | 0.40591
11.5 | 22.3092 | 0.38914
11.6 | 22.4637 | 0.37298
11.7 | 22.638 | 0.35749
11.8 | 22.8321 | 0.34274
11.9 | 23.046 | 0.3288
12 | 23.2797 | 0.31574
12.1 | 23.5331 | 0.30362
12.2 | 23.8064 | 0.29252
12.3 | 24.0995 | 0.28249
12.4 | 24.4123 | 0.27362
12.5 | 24.745 | 0.26597
12.6 | 25.0974 | 0.2596
12.7 | 25.4697 | 0.25459
12.8 | 25.8617 | 0.25101
12.9 | 26.2735 | 0.24891
13 | 26.7052 | 0.24838
13.1 | 27.1566 | 0.24948
13.2 | 27.6278 | 0.25227
13.3 | 28.1188 | 0.25683
13.4 | 28.6296 | 0.26323
13.5 | 29.1602 | 0.27153
13.6 | 29.7106 | 0.2818
13.7 | 30.2808 | 0.29411
13.8 | 30.8707 | 0.30853
13.9 | 31.4805 | 0.32513
14 | 32.1101 | 0.34397
14.1 | 32.7594 | 0.36513
14.2 | 33.4286 | 0.38866
14.3 | 34.1175 | 0.41465
14.4 | 34.8263 | 0.44316
14.5 | 35.5548 | 0.47425
14.6 | 36.3032 | 0.508
14.7 | 37.0713 | 0.54448
14.8 | 37.8592 | 0.58375
14.9 | 38.6669 | 0.62588
15 | 39.4944 | 0.67093
Minimum
Direct Cost
D3

## Risk Model
Coefficients | Activity Risk | Solver: | Risk
a | 0.011404 | 9.4865 | 0.75 | 0.75
b | -0.36329 | 8.2539 | 0.85157 | Max risk
c | 3.6663 | 10.8808 | 0.5 | 0.5
d | -11.0727 | 12.9833 | 0.24836 | Min risk
Duration | Activity Risk
6 | 0.31002
6.1 | 0.3623
6.2 | 0.41148
6.3 | 0.45765
6.4 | 0.50086
6.5 | 0.54118
6.6 | 0.57869
6.7 | 0.61344
6.8 | 0.64551
6.9 | 0.67498
7 | 0.70189
7.1 | 0.72633
7.2 | 0.74836
7.3 | 0.76806
7.4 | 0.78548
7.5 | 0.8007
7.6 | 0.81379
7.7 | 0.82481
7.8 | 0.83383
7.9 | 0.84093
8 | 0.84616
8.1 | 0.84961
8.2 | 0.85133
8.3 | 0.85139
8.4 | 0.84987
8.5 | 0.84683
8.6 | 0.84234
8.7 | 0.83647
8.8 | 0.82929
8.9 | 0.82086
9 | 0.81126
9.1 | 0.80055
9.2 | 0.7888
9.3 | 0.77608
9.4 | 0.76246
9.5 | 0.748
9.6 | 0.73278
9.7 | 0.71686
9.8 | 0.70031
9.9 | 0.6832
10 | 0.66561
10.1 | 0.64758
10.2 | 0.62921
10.3 | 0.61054
10.4 | 0.59166
10.5 | 0.57263
10.6 | 0.55352
10.7 | 0.53439
10.8 | 0.51532
10.9 | 0.49638
11 | 0.47762
11.1 | 0.45913
11.2 | 0.44097
11.3 | 0.4232
11.4 | 0.40591
11.5 | 0.38914
11.6 | 0.37298
11.7 | 0.35749
11.8 | 0.34274
11.9 | 0.3288
12 | 0.31574
12.1 | 0.30362
12.2 | 0.29252
12.3 | 0.28249
12.4 | 0.27362
12.5 | 0.26597
12.6 | 0.2596
12.7 | 0.25459
12.8 | 0.25101
12.9 | 0.24891
13 | 0.24838
13.1 | 0.24948
13.2 | 0.25227
13.3 | 0.25683
13.4 | 0.26323
13.5 | 0.27153
13.6 | 0.2818
13.7 | 0.29411
13.8 | 0.30853
13.9 | 0.32513
14 | 0.34397
14.1 | 0.36513
14.2 | 0.38866
14.3 | 0.41465
14.4 | 0.44316
14.5 | 0.47425
14.6 | 0.508
14.7 | 0.54448
14.8 | 0.58375
14.9 | 0.62588
15 | 0.67093
Simulators
Infra+Clients
Front End
Normal
D4
Minimum Direct Cost
D3
D2
D1
TopDev1+TopDev2
TopDev2
0.75
0.3

## All Points
Coefficients | Direct Cost | Activity Risk | Solver: | Risk
a | 0.98971 | 0.011404 | 9.4865 | 0.75 | 0.75
b | -21.3173 | -0.36329 | 8.2539 | 0.85157 | Max risk
c | 136.5684 | 3.6663 | 10.8808 | 0.5 | 0.5
d |  | -11.0727 | 10.7694 | 0.52114 | Min direct cost
|  |  | 12.9833 | 0.24836 | Min risk
Duration | Direct Cost | Activity Risk | 10.6186 | 0.54996 | Decompression target
6 | 44.2945 | 0.31002
6.1 | 43.3603 | 0.3623
6.2 | 42.4459 | 0.41148
6.3 | 41.5513 | 0.45765
6.4 | 40.6765 | 0.50086
6.5 | 39.8215 | 0.54118
6.6 | 38.9863 | 0.57869
6.7 | 38.1709 | 0.61344
6.8 | 37.3753 | 0.64551
6.9 | 36.5995 | 0.67498
7 | 35.8434 | 0.70189
7.1 | 35.1072 | 0.72633
7.2 | 34.3908 | 0.74836
7.3 | 33.6941 | 0.76806
7.4 | 33.0173 | 0.78548
7.5 | 32.3602 | 0.8007
7.6 | 31.7229 | 0.81379
7.7 | 31.1055 | 0.82481
7.8 | 30.5078 | 0.83383
7.9 | 29.9299 | 0.84093
8 | 29.3718 | 0.84616
8.1 | 28.8335 | 0.84961
8.2 | 28.315 | 0.85133
8.3 | 27.8163 | 0.85139
8.4 | 27.3374 | 0.84987
8.5 | 26.8783 | 0.84683
8.6 | 26.439 | 0.84234
8.7 | 26.0195 | 0.83647
8.8 | 25.6197 | 0.82929
8.9 | 25.2398 | 0.82086
9 | 24.8797 | 0.81126
9.1 | 24.5393 | 0.80055
9.2 | 24.2188 | 0.7888
9.3 | 23.918 | 0.77608
9.4 | 23.637 | 0.76246
9.5 | 23.3759 | 0.748
9.6 | 23.1345 | 0.73278
9.7 | 22.9129 | 0.71686
9.8 | 22.7111 | 0.70031
9.9 | 22.5291 | 0.6832
10 | 22.3669 | 0.66561
10.1 | 22.2245 | 0.64758
10.2 | 22.1019 | 0.62921
10.3 | 21.9991 | 0.61054
10.4 | 21.916 | 0.59166
10.5 | 21.8528 | 0.57263
10.6 | 21.8094 | 0.55352
10.7 | 21.7857 | 0.53439
10.8 | 21.7819 | 0.51532
10.9 | 21.7978 | 0.49638
11 | 21.8336 | 0.47762
11.1 | 21.8891 | 0.45913
11.2 | 21.9644 | 0.44097
11.3 | 22.0596 | 0.4232
11.4 | 22.1745 | 0.40591
11.5 | 22.3092 | 0.38914
11.6 | 22.4637 | 0.37298
11.7 | 22.638 | 0.35749
11.8 | 22.8321 | 0.34274
11.9 | 23.046 | 0.3288
12 | 23.2797 | 0.31574
12.1 | 23.5331 | 0.30362
12.2 | 23.8064 | 0.29252
12.3 | 24.0995 | 0.28249
12.4 | 24.4123 | 0.27362
12.5 | 24.745 | 0.26597
12.6 | 25.0974 | 0.2596
12.7 | 25.4697 | 0.25459
12.8 | 25.8617 | 0.25101
12.9 | 26.2735 | 0.24891
13 | 26.7052 | 0.24838
13.1 | 27.1566 | 0.24948
13.2 | 27.6278 | 0.25227
13.3 | 28.1188 | 0.25683
13.4 | 28.6296 | 0.26323
13.5 | 29.1602 | 0.27153
13.6 | 29.7106 | 0.2818
13.7 | 30.2808 | 0.29411
13.8 | 30.8707 | 0.30853
13.9 | 31.4805 | 0.32513
14 | 32.1101 | 0.34397
14.1 | 32.7594 | 0.36513
14.2 | 33.4286 | 0.38866
14.3 | 34.1175 | 0.41465
14.4 | 34.8263 | 0.44316
14.5 | 35.5548 | 0.47425
14.6 | 36.3032 | 0.508
14.7 | 37.0713 | 0.54448
14.8 | 37.8592 | 0.58375
14.9 | 38.6669 | 0.62588
15 | 39.4944 | 0.67093
Simulators
Infra+Clients
Front End
Normal
D4
Minimum Direct Cost
D3
D2
D1
TopDev1+TopDev2
TopDev2

## Normal
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Critical | Red | Yellow | Green | Criticality Risk | 0.72619 |  |  | Activity Risk | 0.79487 | Fibonacci Formula | 0.6822
| 1 | Requirements | 0 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 65 | 0 | 0 | 0 | 1 | Yellow Factor | 2
| 5 | Test Harness | 65 | 0 | 0 | 0 | 1 | Green Factor | 1
| 6 | Logging | 0 | 1 | 0 | 0 | 0
| 7 | Security | 0 | 1 | 0 | 0 | 0 | Total | 10
| 8 | Pub/Sub | 15 | 0 | 0 | 1 | 0
| 9 | Resource A | 25 | 0 | 0 | 1 | 0 | Critical Limit | 1
| 10 | Resource B | 30 | 0 | 0 | 0 | 1 | Red Limit | 9
| 11 | Resource Access A | 25 | 0 | 0 | 1 | 0 | Yellow Limit | 26
| 12 | Resource Access B | 10 | 0 | 0 | 1 | 0
| 13 | Resource Access C | 0 | 1 | 0 | 0 | 0
| 14 | EngineA | 5 | 0 | 1 | 0 | 0
| 15 | EngineB | 0 | 1 | 0 | 0 | 0
| 16 | EngineC | 30 | 0 | 0 | 0 | 1
| 17 | ManagerA | 0 | 1 | 0 | 0 | 0
| 18 | ManagerB | 5 | 0 | 1 | 0 | 0
| 19 | Client App1 | 5 | 0 | 1 | 0 | 0
| 20 | Client App2 | 0 | 1 | 0 | 0 | 0
| 21 | System Testing | 0 | 1 | 0 | 0 | 0 |  |  | Sanity Check: | Passed
Total |  |  | 280 | 10 | 3 | 4 | 4
21

## Subcritical
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Critical | Red | Yellow | Green | Criticality Risk | 0.78571 |  |  | Activity Risk | 0.78571 | Fibonacci Formula | 0.7662
| 1 | Requirements | 0 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 0 | 1 | 0 | 0 | 0 | Yellow Factor | 2
| 5 | Test Harness | 0 | 1 | 0 | 0 | 0 | Green Factor | 1
| 6 | Logging | 0 | 1 | 0 | 0 | 0
| 7 | Security | 10 | 0 | 0 | 1 | 0 | Total | 10
| 8 | Pub/Sub | 0 | 1 | 0 | 0 | 0
| 9 | Resource A | 0 | 1 | 0 | 0 | 0 | Critical Limit | 1
| 10 | Resource B | 0 | 1 | 0 | 0 | 0 | Red Limit | 9
| 11 | Resource Access A | 0 | 1 | 0 | 0 | 0 | Yellow Limit | 26
| 12 | Resource Access B | 10 | 0 | 0 | 1 | 0
| 13 | Resource Access C | 10 | 0 | 0 | 1 | 0
| 14 | EngineA | 0 | 1 | 0 | 0 | 0
| 15 | EngineB | 60 | 0 | 0 | 0 | 1
| 16 | EngineC | 60 | 0 | 0 | 0 | 1
| 17 | ManagerA | 0 | 1 | 0 | 0 | 0
| 18 | ManagerB | 60 | 0 | 0 | 0 | 1
| 19 | Client App1 | 60 | 0 | 0 | 0 | 1
| 20 | Client App2 | 0 | 1 | 0 | 0 | 0
| 21 | System Testing | 0 | 1 | 0 | 0 | 0 |  |  | Sanity Check: | Passed
Total |  |  |  | 14 | 0 | 3 | 4
21

## TopDev2
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Critical | Red | Yellow | Green | Criticality Risk | 0.70238 |  |  | Activity Risk | 0.77489 | Fibonacci Formula | 0.65972
| 1 | Requirements | 0 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 55 | 0 | 0 | 0 | 1 | Yellow Factor | 2
| 5 | Test Harness | 55 | 0 | 0 | 0 | 1 | Green Factor | 1
| 6 | Logging | 0 | 1 | 0 | 0 | 0
| 7 | Security | 0 | 1 | 0 | 0 | 0 | Total | 10
| 8 | Pub/Sub | 15 | 0 | 0 | 1 | 0
| 9 | Resource A | 30 | 0 | 0 | 0 | 1 | Critical Limit | 1
| 10 | Resource B | 25 | 0 | 0 | 1 | 0 | Red Limit | 9
| 11 | Resource Access A | 30 | 0 | 0 | 0 | 1 | Yellow Limit | 26
| 12 | Resource Access B | 5 | 0 | 1 | 0 | 0
| 13 | Resource Access C | 0 | 1 | 0 | 0 | 0
| 14 | EngineA | 10 | 0 | 0 | 1 | 0
| 15 | EngineB | 0 | 1 | 0 | 0 | 0
| 16 | EngineC | 15 | 0 | 0 | 1 | 0
| 17 | ManagerA | 10 | 0 | 0 | 1 | 0
| 18 | ManagerB | 0 | 1 | 0 | 0 | 0
| 19 | Client App1 | 0 | 1 | 0 | 0 | 0
| 20 | Client App2 | 10 | 0 | 0 | 1 | 0
| 21 | System Testing | 0 | 1 | 0 | 0 | 0 |  |  | Sanity Check: | Passed
Total |  |  | 260 | 10 | 1 | 6 | 4
21

## TopDev1+TopDev2
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Critical | Red | Yellow | Green | Criticality Risk | 0.78571 |  |  | Activity Risk | 0.80272 | Fibonacci Formula | 0.74372
| 1 | Requirements | 0 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 35 | 0 | 0 | 0 | 1 | Yellow Factor | 2
| 5 | Test Harness | 35 | 0 | 0 | 0 | 1 | Green Factor | 1
| 6 | Logging | 0 | 1 | 0 | 0 | 0
| 7 | Security | 0 | 1 | 0 | 0 | 0 | Total | 10
| 8 | Pub/Sub | 10 | 0 | 0 | 1 | 0
| 9 | Resource A | 10 | 0 | 0 | 1 | 0 | Critical Limit | 1
| 10 | Resource B | 10 | 0 | 0 | 1 | 0 | Red Limit | 9
| 11 | Resource Access A | 10 | 0 | 0 | 1 | 0 | Yellow Limit | 26
| 12 | Resource Access B | 0 | 1 | 0 | 0 | 0
| 13 | Resource Access C | 5 | 0 | 1 | 0 | 0
| 14 | EngineA | 5 | 0 | 1 | 0 | 0
| 15 | EngineB | 0 | 1 | 0 | 0 | 0
| 16 | EngineC | 25 | 0 | 0 | 1 | 0
| 17 | ManagerA | 0 | 1 | 0 | 0 | 0
| 18 | ManagerB | 0 | 1 | 0 | 0 | 0
| 19 | Client App1 | 0 | 1 | 0 | 0 | 0
| 20 | Client App2 | 0 | 1 | 0 | 0 | 0
| 21 | System Testing | 0 | 1 | 0 | 0 | 0 |  |  | Sanity Check: | Passed
Total |  |  | 145 | 12 | 2 | 5 | 2
21

## Infra+Clients Front End
[14 empty] | Phi = | 1.618
| ID | Activity | Total Float | Critical | Red | Yellow | Green | Criticality Risk | 0.77174 |  |  | Activity Risk | 0.80978 | Fibonacci Formula | 0.72495
| 1 | Requirements | 0 | 1 | 0 | 0 | 0
| 2 | Architecture | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
| 3 | Project Design | 0 | 1 | 0 | 0 | 0 | Red Factor | 3
| 4 | Test Plan | 20 | 0 | 0 | 1 | 0 | Yellow Factor | 2
| 5 | Test Harness | 20 | 0 | 0 | 1 | 0 | Green Factor | 1
| 6 | Logging | 0 | 1 | 0 | 0 | 0
| 7 | Security | 0 | 1 | 0 | 0 | 0 | Total | 10
| 8 | Pub/Sub | 10 | 0 | 0 | 1 | 0
| 9 | Resource A | 0 | 1 | 0 | 0 | 0 | Critical Limit | 5
| 10 | Resource B | 10 | 0 | 0 | 1 | 0 | Red Limit | 9
| 11 | Resource Access A | 0 | 1 | 0 | 0 | 0 | Yellow Limit | 26
| 12 | Resource Access B | 10 | 0 | 0 | 1 | 0
| 13 | Resource Access C | 20 | 0 | 0 | 1 | 0
| 14 | EngineA | 15 | 0 | 0 | 1 | 0
| 15 | EngineB | 10 | 0 | 0 | 1 | 0
| 16 | EngineC | 40 | 0 | 0 | 0 | 1
| 17 | ManagerA | 0 | 1 | 0 | 0 | 0
| 18 | ManagerB | 10 | 0 | 0 | 1 | 0
| 19 | Client App1 | 5 | 1 | 0 | 0 | 0
| 20 | Client App2 | 0 | 1 | 0 | 0 | 0
| 21 | System Testing | 0 | 1 | 0 | 0 | 0
| 22 | Client App1 Design | 5 | 1 | 0 | 0 | 0
| 23 | Client App2 Design | 0 | 1 | 0 | 0 | 0 |  |  | Sanity Check: | Passed
|  |  | 175 | 13 | 0 | 9 | 1
Total
23
Note on K13: Juval Lowy: Juval Lowy: Due to length of chains, even 5 is considered critical here.

## Simulators
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Critical | Red | Yellow | Green | Criticality Risk | 0.80556 |  |  | Activity Risk | 0.75661 | Fibonacci Formula | 0.78986
1 | Requirements | 0 | 1 | 0 | 0 | 0
2 | Architecture | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
3 | Project Design | 0 | 1 | 0 | 0 | 0 | Red Factor | 3
4 | Test Plan | 5 | 1 | 0 | 0 | 0 | Yellow Factor | 2
5 | Test Harness | 5 | 1 | 0 | 0 | 0 | Green Factor | 1
6 | Logging | 0 | 1 | 0 | 0 | 0
7 | Security | 0 | 1 | 0 | 0 | 0 | Total | 10
8 | Pub/Sub | 10 | 0 | 0 | 1 | 0
9 | Resource A | 0 | 1 | 0 | 0 | 0 | Critical Limit | 5
10 | Resource B | 5 | 1 | 0 | 0 | 0 | Red Limit | 9
11 | Resource Access A | 0 | 1 | 0 | 0 | 0 | Yellow Limit | 26
12 | Resource Access B | 5 | 1 | 0 | 0 | 0
13 | Resource Access C | 15 | 0 | 0 | 1 | 0
14 | EngineA | 15 | 0 | 0 | 1 | 0
15 | EngineB | 5 | 1 | 0 | 0 | 0
16 | EngineC | 35 | 0 | 0 | 0 | 1
17 | ManagerA | 0 | 1 | 0 | 0 | 0
18 | ManagerB | 5 | 1 | 0 | 0 | 0
19 | Client App1 | 0 | 1 | 0 | 0 | 0
20 | Client App2 | 0 | 1 | 0 | 0 | 0
21 | System Testing | 0 | 1 | 0 | 0 | 0
22 | Client App1 Design | 5 | 1 | 0 | 0 | 0
23 | Client App2 Design | 0 | 1 | 0 | 0 | 0
24 | ManagerA Simulator | 30 | 0 | 0 | 0 | 1
25 | ManagerB Simulator | 30 | 0 | 0 | 0 | 1
26 | Client App1 | 30 | 0 | 0 | 0 | 1
27 | Client App2 | 30 | 0 | 0 | 0 | 1 |  |  | Sanity Check: | Passed
|  | 230 | 19 | 0 | 3 | 5
27
Note on K13: Juval Lowy: Juval Lowy: Due to length of chains, even 5 is considered critical here.