## Solutions with Decompression
Design Option | Duration | Direct Cost | Criticality Risk | Activity Risk | Risk Model |  | Indirect cost | Direct Cost | Total Cost
Compressed | 7.1333 | 36.6667 | 0.75 | 0.73377 | 0.74921 |  | 21.8333 |  | 58.5
By Dependencies | 7.8333 | 32 | 0.70455 | 0.69501 | 0.73902 |  | 26.9667 |  | 58.9667
By Layers | 8.0667 | 32.2333 | 0.75568 | 0.75 | 0.68331 |  | 28.6 |  | 60.8333
D1 | 8.3 |  | 0.60227 | 0.6461 | 0.61268
D2 | 8.5333 |  | 0.47727 | 0.56818 | 0.53385
D3 | 9 |  | 0.42045 | 0.45909 | 0.37856 |  | 35.4115 | 32.2299 | 67.6415
D4 | 9.4 |  | 0.26705 | 0.38636 | 0.28166
D5 | 9.9333 | 37.8333 | 0.26705 | 0.34187 | 0.26602 |  | 42.1962 |  | 80.0295
[6 empty] | Min Direct Cost: |  | 31.3503
| Solver: | Risk
| 7.4406 | 0.7804 | Max risk
| 7.774 | 0.75 | 0.75
| 8.4568 | 0.5602 | Min direct cost
| 8.5838 | 0.51637 | Decompression target
| 8.6311 | 0.5 | 0.5
| 9.727 | 0.25234 | Min risk
Activity Risk Adjusting | 1 | (try 0.5 and see)
[8 empty] | Criticality Risk |  | Direct Cost |  | Indirect Cost |  | Total Cost
[8 empty] | a | 0.088361 | a | 2.9808 | a | 7.2692 | a | 2.9808
[8 empty] | b | -2.2754 | b | -50.4167 | b | -30.0115 | b | -43.1474
[8 empty] | c | 19.1854 | c | 244.5315 |  |  | c | 214.52
[8 empty] | d | -52.396
By Layers
By Dependencies
Compressed
D1
D2
D3
D4
D5
Minimum
Decompression
Target

## Cost and Risk Curves
Duration | Direct Cost | Criticality Risk
7 | 37.6762 | 0.714
7.1 | 36.8376 | 0.74174
7.2 | 36.0585 | 0.76162
7.3 | 35.3391 | 0.77416
7.4 | 34.6792 | 0.77989
7.5 | 34.079 | 0.77935
7.6 | 33.5384 | 0.77306
7.7 | 33.0575 | 0.76155
7.8 | 32.6361 | 0.74536
7.9 | 32.2744 | 0.72502
8 | 31.9722 | 0.70104
8.1 | 31.7297 | 0.67398
8.2 | 31.5468 | 0.64434
8.3 | 31.4236 | 0.61268
8.4 | 31.3599 | 0.57951
8.5 | 31.3559 | 0.54536
8.6 | 31.4115 | 0.51077
8.7 | 31.5267 | 0.47626
8.8 | 31.7015 | 0.44237
8.9 | 31.9359 | 0.40963
9 | 32.2299 | 0.37856
9.1 | 32.5836 | 0.3497
9.2 | 32.9969 | 0.32358
9.3 | 33.4698 | 0.30072
9.4 | 34.0023 | 0.28166
9.5 | 34.5944 | 0.26693
9.6 | 35.2462 | 0.25705
9.7 | 35.9575 | 0.25256
9.8 | 36.7285 | 0.25399
9.9 | 37.5591 | 0.26187
10 | 38.4493 | 0.27672
Compressed | 7.1333 | 0.74921
Maximum Risk | 7.4406 | 0.7804
By Dependencies | 7.8333 | 0.73902
By Layers | 8.0667 | 0.68331
Minimum Direct Cost | 8.4568 | 0.5602
D2 | 8.5333 | 0.53385
Decompression Target | 8.5838 | 0.51637
D3 | 9 | 0.37856
Minimum Risk | 9.727 | 0.25234

## Bonus - Crossover Points
Bonus Calculation - Risk Crossover
TMR | 7.4406
R(TMR) | 0.7804
C(TMR) | 34.4281
F | 44.1162
Solver:
Duration | Cross-Over Formula | Risk
7.6401 | 3.6345e-07 | 0.76904
9.4722 | 6.3393e-08 | 0.27056
Too Risky
Too Safe

## Activities Only
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.64205 | Activity Risk | 0.61585 | Fibonacci Formula | 0.62057
2 | Requirements | 15 |  | 15 | 0 | 0 | 1 | 0
3 | Architecture | 0 |  | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
4 | Project Planning | 0 |  | 0 | 1 | 0 | 0 | 0 | Red Factor | 3 | Average | 0.62895
5 | Management Education | 0 |  | 0 | 1 | 0 | 0 | 0 | Yellow Factor | 2
7 | UX Design | 40 |  | 40 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 0 |  | 0 | 1 | 0 | 0 | 0
9 | Test Plan | 65 | 41 | 41 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 65 | 41 | 41 | 0 | 0 | 0 | 1
11 | Build and Setup | 15 |  | 15 | 0 | 0 | 1 | 0
12 | UI Design | 40 |  | 40 | 0 | 0 | 0 | 1 | Red Limit | 9
13 | Manual | 55 | 41 | 41 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 10 |  | 10 | 0 | 0 | 1 | 0
15 | Message Bus | 0 |  | 0 | 1 | 0 | 0 | 0
16 | Security | 0 |  | 0 | 1 | 0 | 0 | 0
18 | Payments DB | 45 | 41 | 41 | 0 | 0 | 0 | 1
19 | Members DB | 30 |  | 30 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
20 | Projects DB | 30 |  | 30 | 0 | 0 | 0 | 1
21 | Contractors DB | 30 |  | 30 | 0 | 0 | 0 | 1
22 | Education DB | 45 | 41 | 41 | 0 | 0 | 0 | 1
23 | Workflows Repository | 0 |  | 0 | 1 | 0 | 0 | 0
24 | Regulations DB | 0 |  | 0 | 1 | 0 | 0 | 0
25 | Data Migration | 90 | 41 | 41 | 0 | 0 | 0 | 1
26 | Payments Access | 45 | 41 | 41 | 0 | 0 | 0 | 1
27 | Members Access | 30 |  | 30 | 0 | 0 | 0 | 1
28 | Projects Access | 30 |  | 30 | 0 | 0 | 0 | 1
29 | Contractors Access | 30 |  | 30 | 0 | 0 | 0 | 1
30 | Education Access | 45 | 41 | 41 | 0 | 0 | 0 | 1
31 | Workflows Access | 0 |  | 0 | 1 | 0 | 0 | 0
32 | Regulations Access | 0 |  | 0 | 1 | 0 | 0 | 0
33 | Regulations Engine A | 0 |  | 0 | 1 | 0 | 0 | 0
34 | Regulations Engine B | 30 |  | 30 | 0 | 0 | 0 | 1
35 | Search Engine | 0 |  | 0 | 1 | 0 | 0 | 0
36 | Abstract Manager | 0 |  | 0 | 1 | 0 | 0 | 0
37 | Membership Manager | 0 |  | 0 | 1 | 0 | 0 | 0
38 | Market Manager | 0 |  | 0 | 1 | 0 | 0 | 0
39 | Education Manager | 0 |  | 0 | 1 | 0 | 0 | 0
40 | Regression Test Harness | 0 |  | 0 | 1 | 0 | 0 | 0
42 | Members Portal | 10 |  | 10 | 0 | 0 | 1 | 0
43 | Contractors Portal | 10 |  | 10 | 0 | 0 | 1 | 0
44 | Education Portal | 15 |  | 15 | 0 | 0 | 1 | 0
45 | Marketplace App | 0 |  | 0 | 1 | 0 | 0 | 0
46 | Manual Polishing | 0 |  | 0 | 1 | 0 | 0 | 0
47 | System Testing | 0 |  | 0 | 1 | 0 | 0 | 0
48 | System Roolout | 0 |  | 0 | 1 | 0 | 0 | 0

## Compressed
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.75 | Activity Risk | 0.73377 | Fibonacci Formula | 0.69279
2 | Requirements | 15 |  | 15 | 0 | 0 | 1 | 0
3 | Architecture | 0 |  | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
4 | Project Planning | 0 |  | 0 | 1 | 0 | 0 | 0 | Red Factor | 3
5 | Management Education | 0 |  | 0 | 1 | 0 | 0 | 0 | Yellow Factor | 2
7 | UX Design | 30 | 28 | 28 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 5 |  | 5 | 0 | 1 | 0 | 0
9 | Test Plan | 50 | 28 | 28 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 50 | 28 | 28 | 0 | 0 | 0 | 1
11 | Build and Setup | 30 | 28 | 28 | 0 | 0 | 0 | 1
12 | UI Design | 0 |  | 0 | 1 | 0 | 0 | 0 | Red Limit | 9
13 | Manual | 35 | 28 | 28 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 5 |  | 5 | 0 | 1 | 0 | 0
15 | Message Bus | 5 |  | 5 | 0 | 1 | 0 | 0
16 | Security | 5 |  | 5 | 0 | 1 | 0 | 0
18 | Payments DB | 0 |  | 0 | 1 | 0 | 0 | 0
19 | Members DB | 0 |  | 0 | 1 | 0 | 0 | 0 | Sanity Check: | Passed
20 | Projects DB | 0 |  | 0 | 1 | 0 | 0 | 0
21 | Contractors DB | 0 |  | 0 | 1 | 0 | 0 | 0
22 | Education DB | 0 |  | 0 | 1 | 0 | 0 | 0
23 | Workflows Repository | 5 |  | 5 | 0 | 1 | 0 | 0
24 | Regulations DB | 0 |  | 0 | 1 | 0 | 0 | 0
25 | Data Migration | 70 | 28 | 28 | 0 | 0 | 0 | 1
26 | Payments Access | 0 |  | 0 | 1 | 0 | 0 | 0
27 | Members Access | 0 |  | 0 | 1 | 0 | 0 | 0
28 | Projects Access | 45 | 28 | 28 | 0 | 0 | 0 | 1
29 | Contractors Access | 45 | 28 | 28 | 0 | 0 | 0 | 1
30 | Education Access | 55 | 28 | 28 | 0 | 0 | 0 | 1
31 | Workflows Access | 5 |  | 5 | 0 | 1 | 0 | 0
32 | Regulations Access | 0 |  | 0 | 1 | 0 | 0 | 0
33 | Regulations Engine A | 5 |  | 5 | 0 | 1 | 0 | 0
34 | Regulations Engine B | 5 |  | 5 | 0 | 1 | 0 | 0
35 | Search Engine | 0 |  | 0 | 1 | 0 | 0 | 0
36 | Abstract Manager | 5 |  | 5 | 0 | 1 | 0 | 0
37 | Membership Manager | 5 |  | 5 | 0 | 1 | 0 | 0
38 | Market Manager | 0 |  | 0 | 1 | 0 | 0 | 0
39 | Education Manager | 5 |  | 5 | 0 | 1 | 0 | 0
40 | Notification Manager | 5 |  | 5 | 0 | 1 | 0 | 0
41 | Membership Manager Contract | 5 |  | 5 | 0 | 1 | 0 | 0
42 | Market Manager Contract | 5 |  | 5 | 0 | 1 | 0 | 0
43 | Education Manager Contract | 0 |  | 0 | 1 | 0 | 0 | 0
44 | Regression Test Harness Design | 50 | 28 | 28 | 0 | 0 | 0 | 1
45 | Membership Manager Simulator | 0 |  | 0 | 1 | 0 | 0 | 0
46 | Market Manager Simulator | 5 |  | 5 | 0 | 1 | 0 | 0
47 | Education Manager Simulator | 5 |  | 5 | 0 | 1 | 0 | 0
48 | Members Portal | 0 |  | 0 | 1 | 0 | 0 | 0
49 | Contractors Portal | 0 |  | 0 | 1 | 0 | 0 | 0
50 | Education Portal | 5 |  | 5 | 0 | 1 | 0 | 0
51 | Marketplace App | 5 |  | 5 | 0 | 1 | 0 | 0
52 | Members Portal Integration | 5 |  | 5 | 0 | 1 | 0 | 0
53 | Contractors Portal Integration | 0 |  | 0 | 1 | 0 | 0 | 0
54 | Education Portal Integration | 5 |  | 5 | 0 | 1 | 0 | 0
55 | Marketplace Apps Integration | 5 |  | 5 | 0 | 1 | 0 | 0
56 | Manual Polishing | 10 |  | 10 | 0 | 0 | 1 | 0
57 | System Testing | 0 |  | 0 | 1 | 0 | 0 | 0
58 | System Roolout | 0 |  | 0 | 1 | 0 | 0 | 0

## By Dependencies
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.70455 | Activity Risk | 0.69501 | Fibonacci Formula | 0.65704
2 | Requirements | 15 |  | 15 | 0 | 0 | 1 | 0
3 | Architecture | 0 |  | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
4 | Project Planning | 0 |  | 0 | 1 | 0 | 0 | 0 | Red Factor | 3 | Average | 0.69978
5 | Management Education | 0 |  | 0 | 1 | 0 | 0 | 0 | Yellow Factor | 2
7 | UX Design | 40 | 31 | 31 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 0 |  | 0 | 1 | 0 | 0 | 0
9 | Test Plan | 65 | 31 | 31 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 65 | 31 | 31 | 0 | 0 | 0 | 1
11 | Build and Setup | 15 |  | 15 | 0 | 0 | 1 | 0
12 | UI Design | 40 | 31 | 31 | 0 | 0 | 0 | 1 | Red Limit | 9
13 | Manual | 55 | 31 | 31 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 10 |  | 10 | 0 | 0 | 1 | 0
15 | Message Bus | 0 |  | 0 | 1 | 0 | 0 | 0
16 | Security | 0 |  | 0 | 1 | 0 | 0 | 0
18 | Payments DB | 20 |  | 20 | 0 | 0 | 1 | 0
19 | Members DB | 10 |  | 10 | 0 | 0 | 1 | 0 | Sanity Check: | Passed
20 | Projects DB | 10 |  | 10 | 0 | 0 | 1 | 0
21 | Contractors DB | 15 |  | 15 | 0 | 0 | 1 | 0
22 | Education DB | 20 |  | 20 | 0 | 0 | 1 | 0
23 | Workflows Repository | 0 |  | 0 | 1 | 0 | 0 | 0
24 | Regulations DB | 0 |  | 0 | 1 | 0 | 0 | 0
25 | Data Migration | 65 | 31 | 31 | 0 | 0 | 0 | 1
26 | Payments Access | 20 |  | 20 | 0 | 0 | 1 | 0
27 | Members Access | 15 |  | 15 | 0 | 0 | 1 | 0
28 | Projects Access | 10 |  | 10 | 0 | 0 | 1 | 0
29 | Contractors Access | 15 |  | 15 | 0 | 0 | 1 | 0
30 | Education Access | 10 |  | 10 | 0 | 0 | 1 | 0
31 | Workflows Access | 0 |  | 0 | 1 | 0 | 0 | 0
32 | Regulations Access | 0 |  | 0 | 1 | 0 | 0 | 0
33 | Regulations Engine A | 0 |  | 0 | 1 | 0 | 0 | 0
34 | Regulations Engine B | 0 |  | 0 | 1 | 0 | 0 | 0
35 | Search Engine | 10 |  | 10 | 0 | 0 | 1 | 0
36 | Abstract Manager | 0 |  | 0 | 1 | 0 | 0 | 0
37 | Membership Manager | 0 |  | 0 | 1 | 0 | 0 | 0
38 | Market Manager | 0 |  | 0 | 1 | 0 | 0 | 0
39 | Education Manager | 0 |  | 0 | 1 | 0 | 0 | 0
40 | Regression Test Harness | 0 |  | 0 | 1 | 0 | 0 | 0
42 | Members Portal | 10 |  | 10 | 0 | 0 | 1 | 0
43 | Contractors Portal | 10 |  | 10 | 0 | 0 | 1 | 0
44 | Education Portal | 15 |  | 15 | 0 | 0 | 1 | 0
45 | Marketplace App | 0 |  | 0 | 1 | 0 | 0 | 0
46 | Manual Polishing | 0 |  | 0 | 1 | 0 | 0 | 0
47 | System Testing | 0 |  | 0 | 1 | 0 | 0 | 0
48 | System Roolout | 0 |  | 0 | 1 | 0 | 0 | 0

## By Layers (Normal)
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.75568 | Activity Risk | 0.75 | Fibonacci Formula | 0.71196
2 | Requirements | 15 |  | 15 | 0 | 0 | 1 | 0
3 | Architecture | 0 |  | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
4 | Project Planning | 0 |  | 0 | 1 | 0 | 0 | 0 | Red Factor | 3 | Average | 0.75284
5 | Management Education | 0 |  | 0 | 1 | 0 | 0 | 0 | Yellow Factor | 2
7 | UX Design | 45 | 30 | 30 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 0 |  | 0 | 1 | 0 | 0 | 0
9 | Test Plan | 70 | 30 | 30 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 70 | 30 | 30 | 0 | 0 | 0 | 1
11 | Build and Setup | 15 |  | 15 | 0 | 0 | 1 | 0
12 | UI Design | 45 | 30 | 30 | 0 | 0 | 0 | 1 | Red Limit | 9
13 | Manual | 60 | 30 | 30 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 10 |  | 10 | 0 | 0 | 1 | 0
15 | Message Bus | 5 |  | 5 | 0 | 1 | 0 | 0
16 | Security | 0 |  | 0 | 1 | 0 | 0 | 0
18 | Payments DB | 5 |  | 5 | 0 | 1 | 0 | 0
19 | Members DB | 5 |  | 5 | 0 | 1 | 0 | 0 | Sanity Check: | Passed
20 | Projects DB | 10 |  | 10 | 0 | 0 | 1 | 0
21 | Contractors DB | 10 |  | 10 | 0 | 0 | 1 | 0
22 | Education DB | 5 |  | 5 | 0 | 1 | 0 | 0
23 | Workflows Repository | 0 |  | 0 | 1 | 0 | 0 | 0
24 | Regulations DB | 5 |  | 5 | 0 | 1 | 0 | 0
26 | Data Migration | 50 | 30 | 30 | 0 | 0 | 0 | 1
27 | Payments Access | 0 |  | 0 | 1 | 0 | 0 | 0
28 | Members Access | 0 |  | 0 | 1 | 0 | 0 | 0
29 | Projects Access | 0 |  | 0 | 1 | 0 | 0 | 0
30 | Contractors Access | 0 |  | 0 | 1 | 0 | 0 | 0
31 | Education Access | 0 |  | 0 | 1 | 0 | 0 | 0
32 | Workflows Access | 0 |  | 0 | 1 | 0 | 0 | 0
33 | Regulations Access | 0 |  | 0 | 1 | 0 | 0 | 0
35 | Regulations Engine A | 0 |  | 0 | 1 | 0 | 0 | 0
36 | Regulations Engine B | 15 |  | 15 | 0 | 0 | 1 | 0
37 | Search Engine | 15 |  | 15 | 0 | 0 | 1 | 0
39 | Abstract Manager | 0 |  | 0 | 1 | 0 | 0 | 0
40 | Membership Manager | 0 |  | 0 | 1 | 0 | 0 | 0
41 | Market Manager | 0 |  | 0 | 1 | 0 | 0 | 0
42 | Education Manager | 0 |  | 0 | 1 | 0 | 0 | 0
43 | Regression Test Harness | 0 |  | 0 | 1 | 0 | 0 | 0
45 | Members Portal | 10 |  | 10 | 0 | 0 | 1 | 0
46 | Contractors Portal | 10 |  | 10 | 0 | 0 | 1 | 0
47 | Education Portal | 15 |  | 15 | 0 | 0 | 1 | 0
48 | Marketplace App | 0 |  | 0 | 1 | 0 | 0 | 0
50 | Manual Polishing | 0 |  | 0 | 1 | 0 | 0 | 0
51 | System Testing | 0 |  | 0 | 1 | 0 | 0 | 0
52 | System Rollout | 0 |  | 0 | 1 | 0 | 0 | 0

## By Layers Subcritical
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.81818 | Activity Risk | 0.84563 | Fibonacci Formula | 0.78882
2 | Requirements | 15 |  | 15 | 0 | 0 | 1 | 0
3 | Architecture | 0 |  | 0 | 1 | 0 | 0 | 0 | Critical factor | 4
4 | Project Planning | 0 |  | 0 | 1 | 0 | 0 | 0 | Red Factor | 3 | Average | 0.8319
5 | Management Education | 0 |  | 0 | 1 | 0 | 0 | 0 | Yellow Factor | 2
7 | UX Design | 100 | 53 | 53 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 0 |  | 0 | 1 | 0 | 0 | 0
9 | Test Plan | 135 | 53 | 53 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 135 | 53 | 53 | 0 | 0 | 0 | 1
11 | Build and Setup | 15 |  | 15 | 0 | 0 | 1 | 0
12 | UI Design | 100 | 53 | 53 | 0 | 0 | 0 | 1 | Red Limit | 9
13 | Manual | 125 | 53 | 53 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 10 |  | 10 | 0 | 0 | 1 | 0
15 | Message Bus | 5 |  | 5 | 0 | 1 | 0 | 0
16 | Security | 0 |  | 0 | 1 | 0 | 0 | 0
18 | Payments DB | 0 |  | 0 | 1 | 0 | 0 | 0
19 | Members DB | 0 |  | 0 | 1 | 0 | 0 | 0 | Sanity Check: | Passed
20 | Projects DB | 0 |  | 0 | 1 | 0 | 0 | 0
21 | Contractors DB | 0 |  | 0 | 1 | 0 | 0 | 0
22 | Education DB | 0 |  | 0 | 1 | 0 | 0 | 0
23 | Workflows Repository | 0 |  | 0 | 1 | 0 | 0 | 0
24 | Regulations DB | 0 |  | 0 | 1 | 0 | 0 | 0
26 | Data Migration | 10 |  | 10 | 0 | 0 | 1 | 0
27 | Payments Access | 10 |  | 10 | 0 | 0 | 1 | 0
28 | Members Access | 0 |  | 0 | 1 | 0 | 0 | 0
29 | Projects Access | 0 |  | 0 | 1 | 0 | 0 | 0
30 | Contractors Access | 10 |  | 10 | 0 | 0 | 1 | 0
31 | Education Access | 0 |  | 0 | 1 | 0 | 0 | 0
32 | Workflows Access | 0 |  | 0 | 1 | 0 | 0 | 0
33 | Regulations Access | 10 |  | 10 | 0 | 0 | 1 | 0
35 | Regulations Engine A | 0 |  | 0 | 1 | 0 | 0 | 0
36 | Regulations Engine B | 0 |  | 0 | 1 | 0 | 0 | 0
37 | Search Engine | 0 |  | 0 | 1 | 0 | 0 | 0
39 | Abstract Manager | 0 |  | 0 | 1 | 0 | 0 | 0
40 | Membership Manager | 0 |  | 0 | 1 | 0 | 0 | 0
41 | Market Manager | 0 |  | 0 | 1 | 0 | 0 | 0
42 | Education Manager | 0 |  | 0 | 1 | 0 | 0 | 0
43 | Regression Test Harness | 0 |  | 0 | 1 | 0 | 0 | 0
45 | Members Portal | 5 |  | 5 | 0 | 1 | 0 | 0
46 | Contractors Portal | 5 |  | 5 | 0 | 1 | 0 | 0
47 | Education Portal | 0 |  | 0 | 1 | 0 | 0 | 0
48 | Marketplace App | 0 |  | 0 | 1 | 0 | 0 | 0
50 | Manual Polishing | 0 |  | 0 | 1 | 0 | 0 | 0
51 | System Testing | 0 |  | 0 | 1 | 0 | 0 | 0
52 | System Rollout | 0 |  | 0 | 1 | 0 | 0 | 0

## D1
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.60227 | Activity Risk | 0.6461 | Fibonacci Formula | 0.49415
2 | Requirements | 20 |  | 20 | 0 | 0 | 1 | 0
3 | Architecture | 5 |  | 5 | 0 | 1 | 0 | 0 | Critical factor | 4
4 | Project Planning | 5 |  | 5 | 0 | 1 | 0 | 0 | Red Factor | 3 | Average | 0.62419
5 | Management Education | 5 |  | 5 | 0 | 1 | 0 | 0 | Yellow Factor | 2
7 | UX Design | 50 | 35 | 35 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 5 |  | 5 | 0 | 1 | 0 | 0 |  |  | Culling Factor | 1
9 | Test Plan | 75 | 35 | 35 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 75 | 35 | 35 | 0 | 0 | 0 | 1
11 | Build and Setup | 20 |  | 20 | 0 | 0 | 1 | 0
12 | UI Design | 50 | 35 | 35 | 0 | 0 | 0 | 1 | Red Limit | 9
13 | Manual | 65 | 35 | 35 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 15 |  | 15 | 0 | 0 | 1 | 0
15 | Message Bus | 10 |  | 10 | 0 | 0 | 1 | 0
16 | Security | 5 |  | 5 | 0 | 1 | 0 | 0
18 | Payments DB | 10 |  | 10 | 0 | 0 | 1 | 0
19 | Members DB | 10 |  | 10 | 0 | 0 | 1 | 0 | Sanity Check: | Passed
20 | Projects DB | 15 |  | 15 | 0 | 0 | 1 | 0
21 | Contractors DB | 15 |  | 15 | 0 | 0 | 1 | 0
22 | Education DB | 10 |  | 10 | 0 | 0 | 1 | 0 | Decompressed by 1 week to finish 9/11/15
23 | Workflows Repository | 5 |  | 5 | 0 | 1 | 0 | 0
24 | Regulations DB | 10 |  | 10 | 0 | 0 | 1 | 0
26 | Data Migration | 55 | 35 | 35 | 0 | 0 | 0 | 1
27 | Payments Access | 5 |  | 5 | 0 | 1 | 0 | 0
28 | Members Access | 5 |  | 5 | 0 | 1 | 0 | 0
29 | Projects Access | 5 |  | 5 | 0 | 1 | 0 | 0
30 | Contractors Access | 5 |  | 5 | 0 | 1 | 0 | 0
31 | Education Access | 5 |  | 5 | 0 | 1 | 0 | 0
32 | Workflows Access | 5 |  | 5 | 0 | 1 | 0 | 0
33 | Regulations Access | 5 |  | 5 | 0 | 1 | 0 | 0
35 | Regulations Engine A | 5 |  | 5 | 0 | 1 | 0 | 0
36 | Regulations Engine B | 20 |  | 20 | 0 | 0 | 1 | 0
37 | Search Engine | 20 |  | 20 | 0 | 0 | 1 | 0
39 | Abstract Manager | 5 |  | 5 | 0 | 1 | 0 | 0
40 | Membership Manager | 5 |  | 5 | 0 | 1 | 0 | 0
41 | Market Manager | 5 |  | 5 | 0 | 1 | 0 | 0
42 | Education Manager | 5 |  | 5 | 0 | 1 | 0 | 0
43 | Regression Test Harness | 5 |  | 5 | 0 | 1 | 0 | 0
45 | Members Portal | 15 |  | 15 | 0 | 0 | 1 | 0
46 | Contractors Portal | 15 |  | 15 | 0 | 0 | 1 | 0
47 | Education Portal | 20 |  | 20 | 0 | 0 | 1 | 0
48 | Marketplace App | 5 |  | 5 | 0 | 1 | 0 | 0
50 | Manual Polishing | 5 |  | 5 | 0 | 1 | 0 | 0
51 | System Testing | 5 |  | 5 | 0 | 1 | 0 | 0
52 | System Rollout | 0 |  | 0 | 1 | 0 | 0 | 0

## D2
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.47727 | Activity Risk | 0.56818 | Fibonacci Formula | 0.37612
2 | Requirements | 25 |  | 25 | 0 | 0 | 1 | 0
3 | Architecture | 10 |  | 10 | 0 | 0 | 1 | 0 | Critical factor | 4
4 | Project Planning | 10 |  | 10 | 0 | 0 | 1 | 0 | Red Factor | 3 | Average | 0.52273
5 | Management Education | 10 |  | 10 | 0 | 0 | 1 | 0 | Yellow Factor | 2
7 | UX Design | 55 | 40 | 40 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 10 |  | 10 | 0 | 0 | 1 | 0 |  |  | Culling Factor | 1
9 | Test Plan | 80 | 40 | 40 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 80 | 40 | 40 | 0 | 0 | 0 | 1
11 | Build and Setup | 25 |  | 25 | 0 | 0 | 1 | 0
12 | UI Design | 55 | 40 | 40 | 0 | 0 | 0 | 1 | Red Limit | 9
13 | Manual | 70 | 40 | 40 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 20 |  | 20 | 0 | 0 | 1 | 0
15 | Message Bus | 15 |  | 15 | 0 | 0 | 1 | 0
16 | Security | 10 |  | 10 | 0 | 0 | 1 | 0
18 | Payments DB | 15 |  | 15 | 0 | 0 | 1 | 0
19 | Members DB | 15 |  | 15 | 0 | 0 | 1 | 0 | Sanity Check: | Passed
20 | Projects DB | 20 |  | 20 | 0 | 0 | 1 | 0
21 | Contractors DB | 20 |  | 20 | 0 | 0 | 1 | 0
22 | Education DB | 15 |  | 15 | 0 | 0 | 1 | 0 | Decompressed by 2 weeks to finish 9/18/15
23 | Workflows Repository | 10 |  | 10 | 0 | 0 | 1 | 0
24 | Regulations DB | 15 |  | 15 | 0 | 0 | 1 | 0
26 | Data Migration | 60 | 40 | 40 | 0 | 0 | 0 | 1
27 | Payments Access | 10 |  | 10 | 0 | 0 | 1 | 0
28 | Members Access | 10 |  | 10 | 0 | 0 | 1 | 0
29 | Projects Access | 10 |  | 10 | 0 | 0 | 1 | 0
30 | Contractors Access | 10 |  | 10 | 0 | 0 | 1 | 0
31 | Education Access | 10 |  | 10 | 0 | 0 | 1 | 0
32 | Workflows Access | 10 |  | 10 | 0 | 0 | 1 | 0
33 | Regulations Access | 10 |  | 10 | 0 | 0 | 1 | 0
35 | Regulations Engine A | 10 |  | 10 | 0 | 0 | 1 | 0
36 | Regulations Engine B | 25 |  | 25 | 0 | 0 | 1 | 0
37 | Search Engine | 25 |  | 25 | 0 | 0 | 1 | 0
39 | Abstract Manager | 10 |  | 10 | 0 | 0 | 1 | 0
40 | Membership Manager | 10 |  | 10 | 0 | 0 | 1 | 0
41 | Market Manager | 10 |  | 10 | 0 | 0 | 1 | 0
42 | Education Manager | 10 |  | 10 | 0 | 0 | 1 | 0
43 | Regression Test Harness | 10 |  | 10 | 0 | 0 | 1 | 0
45 | Members Portal | 20 |  | 20 | 0 | 0 | 1 | 0
46 | Contractors Portal | 20 |  | 20 | 0 | 0 | 1 | 0
47 | Education Portal | 25 |  | 25 | 0 | 0 | 1 | 0
48 | Marketplace App | 10 |  | 10 | 0 | 0 | 1 | 0
50 | Manual Polishing | 10 |  | 10 | 0 | 0 | 1 | 0
51 | System Testing | 10 |  | 10 | 0 | 0 | 1 | 0
52 | System Rollout | 0 |  | 0 | 1 | 0 | 0 | 0

## D3
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.42045 | Activity Risk | 0.45909 | Fibonacci Formula | 0.34296
2 | Requirements | 35 |  | 35 | 0 | 0 | 0 | 1
3 | Architecture | 20 |  | 20 | 0 | 0 | 1 | 0 | Critical factor | 4
4 | Project Planning | 20 |  | 20 | 0 | 0 | 1 | 0 | Red Factor | 3 | Average | 0.43977
5 | Management Education | 20 |  | 20 | 0 | 0 | 1 | 0 | Yellow Factor | 2
7 | UX Design | 65 | 50 | 50 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 20 |  | 20 | 0 | 0 | 1 | 0 |  |  | Culling Factor | 1
9 | Test Plan | 90 | 50 | 50 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 90 | 50 | 50 | 0 | 0 | 0 | 1
11 | Build and Setup | 35 |  | 35 | 0 | 0 | 0 | 1
12 | UI Design | 65 | 50 | 50 | 0 | 0 | 0 | 1 | Red Limit | 9
13 | Manual | 80 | 50 | 50 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 30 |  | 30 | 0 | 0 | 0 | 1
15 | Message Bus | 25 |  | 25 | 0 | 0 | 1 | 0
16 | Security | 20 |  | 20 | 0 | 0 | 1 | 0
18 | Payments DB | 25 |  | 25 | 0 | 0 | 1 | 0
19 | Members DB | 25 |  | 25 | 0 | 0 | 1 | 0 | Sanity Check: | Passed
20 | Projects DB | 30 |  | 30 | 0 | 0 | 0 | 1
21 | Contractors DB | 30 |  | 30 | 0 | 0 | 0 | 1
22 | Education DB | 25 |  | 25 | 0 | 0 | 1 | 0 | Decompressed by 4 weeks to finish 9/25/15
23 | Workflows Repository | 20 |  | 20 | 0 | 0 | 1 | 0
24 | Regulations DB | 25 |  | 25 | 0 | 0 | 1 | 0
26 | Data Migration | 70 | 50 | 50 | 0 | 0 | 0 | 1
27 | Payments Access | 20 |  | 20 | 0 | 0 | 1 | 0
28 | Members Access | 20 |  | 20 | 0 | 0 | 1 | 0
29 | Projects Access | 20 |  | 20 | 0 | 0 | 1 | 0
30 | Contractors Access | 20 |  | 20 | 0 | 0 | 1 | 0
31 | Education Access | 20 |  | 20 | 0 | 0 | 1 | 0
32 | Workflows Access | 20 |  | 20 | 0 | 0 | 1 | 0
33 | Regulations Access | 20 |  | 20 | 0 | 0 | 1 | 0
35 | Regulations Engine A | 20 |  | 20 | 0 | 0 | 1 | 0
36 | Regulations Engine B | 35 |  | 35 | 0 | 0 | 0 | 1
37 | Search Engine | 35 |  | 35 | 0 | 0 | 0 | 1
39 | Abstract Manager | 20 |  | 20 | 0 | 0 | 1 | 0
40 | Membership Manager | 20 |  | 20 | 0 | 0 | 1 | 0
41 | Market Manager | 20 |  | 20 | 0 | 0 | 1 | 0
42 | Education Manager | 20 |  | 20 | 0 | 0 | 1 | 0
43 | Regression Test Harness | 20 |  | 20 | 0 | 0 | 1 | 0
45 | Members Portal | 30 |  | 30 | 0 | 0 | 0 | 1
46 | Contractors Portal | 30 |  | 30 | 0 | 0 | 0 | 1
47 | Education Portal | 35 |  | 35 | 0 | 0 | 0 | 1
48 | Marketplace App | 20 |  | 20 | 0 | 0 | 1 | 0
50 | Manual Polishing | 20 |  | 20 | 0 | 0 | 1 | 0
51 | System Testing | 20 |  | 20 | 0 | 0 | 1 | 0
52 | System Rollout | 0 |  | 0 | 1 | 0 | 0 | 0

## D4
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.26705 | Activity Risk | 0.38636 | Fibonacci Formula | 0.25343
2 | Requirements | 45 |  | 45 | 0 | 0 | 0 | 1
3 | Architecture | 30 |  | 30 | 0 | 0 | 0 | 1 | Critical factor | 4
4 | Project Planning | 30 |  | 30 | 0 | 0 | 0 | 1 | Red Factor | 3 | Average | 0.3267
5 | Management Education | 30 |  | 30 | 0 | 0 | 0 | 1 | Yellow Factor | 2
7 | UX Design | 75 | 60 | 60 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 30 |  | 30 | 0 | 0 | 0 | 1 |  |  | Culling Factor | 1
9 | Test Plan | 100 | 60 | 60 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 100 | 60 | 60 | 0 | 0 | 0 | 1
11 | Build and Setup | 45 |  | 45 | 0 | 0 | 0 | 1
12 | UI Design | 75 | 60 | 60 | 0 | 0 | 0 | 1 | Red Limit | 9
13 | Manual | 90 | 60 | 60 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 40 |  | 40 | 0 | 0 | 0 | 1
15 | Message Bus | 35 |  | 35 | 0 | 0 | 0 | 1
16 | Security | 30 |  | 30 | 0 | 0 | 0 | 1
18 | Payments DB | 35 |  | 35 | 0 | 0 | 0 | 1
19 | Members DB | 35 |  | 35 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
20 | Projects DB | 40 |  | 40 | 0 | 0 | 0 | 1
21 | Contractors DB | 40 |  | 40 | 0 | 0 | 0 | 1
22 | Education DB | 35 |  | 35 | 0 | 0 | 0 | 1 | Decompressed by 6 weeks to finish 10/16/15
23 | Workflows Repository | 30 |  | 30 | 0 | 0 | 0 | 1
24 | Regulations DB | 35 |  | 35 | 0 | 0 | 0 | 1
26 | Data Migration | 80 | 60 | 60 | 0 | 0 | 0 | 1
27 | Payments Access | 30 |  | 30 | 0 | 0 | 0 | 1
28 | Members Access | 30 |  | 30 | 0 | 0 | 0 | 1
29 | Projects Access | 30 |  | 30 | 0 | 0 | 0 | 1
30 | Contractors Access | 30 |  | 30 | 0 | 0 | 0 | 1
31 | Education Access | 30 |  | 30 | 0 | 0 | 0 | 1
32 | Workflows Access | 30 |  | 30 | 0 | 0 | 0 | 1
33 | Regulations Access | 30 |  | 30 | 0 | 0 | 0 | 1
35 | Regulations Engine A | 30 |  | 30 | 0 | 0 | 0 | 1
36 | Regulations Engine B | 45 |  | 45 | 0 | 0 | 0 | 1
37 | Search Engine | 45 |  | 45 | 0 | 0 | 0 | 1
39 | Abstract Manager | 30 |  | 30 | 0 | 0 | 0 | 1
40 | Membership Manager | 30 |  | 30 | 0 | 0 | 0 | 1
41 | Market Manager | 30 |  | 30 | 0 | 0 | 0 | 1
42 | Education Manager | 30 |  | 30 | 0 | 0 | 0 | 1
43 | Regression Test Harness | 30 |  | 30 | 0 | 0 | 0 | 1
45 | Members Portal | 40 |  | 40 | 0 | 0 | 0 | 1
46 | Contractors Portal | 40 |  | 40 | 0 | 0 | 0 | 1
47 | Education Portal | 45 |  | 45 | 0 | 0 | 0 | 1
48 | Marketplace App | 30 |  | 30 | 0 | 0 | 0 | 1
50 | Manual Polishing | 30 |  | 30 | 0 | 0 | 0 | 1
51 | System Testing | 30 |  | 30 | 0 | 0 | 0 | 1
52 | System Rollout | 0 |  | 0 | 1 | 0 | 0 | 0

## D5
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.26705 | Activity Risk | 0.34187 | Fibonacci Formula | 0.25343
2 | Requirements | 55 |  | 55 | 0 | 0 | 0 | 1
3 | Architecture | 40 |  | 40 | 0 | 0 | 0 | 1 | Critical factor | 4
4 | Project Planning | 40 |  | 40 | 0 | 0 | 0 | 1 | Red Factor | 3 | Average | 0.30446
5 | Management Education | 40 |  | 40 | 0 | 0 | 0 | 1 | Yellow Factor | 2
7 | UX Design | 85 | 71 | 71 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 40 |  | 40 | 0 | 0 | 0 | 1 |  |  | Culling Factor | 1
9 | Test Plan | 110 | 71 | 71 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 110 | 71 | 71 | 0 | 0 | 0 | 1
11 | Build and Setup | 55 |  | 55 | 0 | 0 | 0 | 1
12 | UI Design | 85 | 71 | 71 | 0 | 0 | 0 | 1 | Red Limit | 9
13 | Manual | 100 | 71 | 71 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 50 |  | 50 | 0 | 0 | 0 | 1
15 | Message Bus | 45 |  | 45 | 0 | 0 | 0 | 1
16 | Security | 40 |  | 40 | 0 | 0 | 0 | 1
18 | Payments DB | 45 |  | 45 | 0 | 0 | 0 | 1
19 | Members DB | 45 |  | 45 | 0 | 0 | 0 | 1 | Sanity Check: | Passed
20 | Projects DB | 50 |  | 50 | 0 | 0 | 0 | 1
21 | Contractors DB | 50 |  | 50 | 0 | 0 | 0 | 1
22 | Education DB | 45 |  | 45 | 0 | 0 | 0 | 1 | Decompressed by 8 weeks to finish 10/30/15
23 | Workflows Repository | 40 |  | 40 | 0 | 0 | 0 | 1
24 | Regulations DB | 45 |  | 45 | 0 | 0 | 0 | 1
26 | Data Migration | 90 | 71 | 71 | 0 | 0 | 0 | 1
27 | Payments Access | 40 |  | 40 | 0 | 0 | 0 | 1
28 | Members Access | 40 |  | 40 | 0 | 0 | 0 | 1
29 | Projects Access | 40 |  | 40 | 0 | 0 | 0 | 1
30 | Contractors Access | 40 |  | 40 | 0 | 0 | 0 | 1
31 | Education Access | 40 |  | 40 | 0 | 0 | 0 | 1
32 | Workflows Access | 40 |  | 40 | 0 | 0 | 0 | 1
33 | Regulations Access | 40 |  | 40 | 0 | 0 | 0 | 1
35 | Regulations Engine A | 40 |  | 40 | 0 | 0 | 0 | 1
36 | Regulations Engine B | 55 |  | 55 | 0 | 0 | 0 | 1
37 | Search Engine | 55 |  | 55 | 0 | 0 | 0 | 1
39 | Abstract Manager | 40 |  | 40 | 0 | 0 | 0 | 1
40 | Membership Manager | 40 |  | 40 | 0 | 0 | 0 | 1
41 | Market Manager | 40 |  | 40 | 0 | 0 | 0 | 1
42 | Education Manager | 40 |  | 40 | 0 | 0 | 0 | 1
43 | Regression Test Harness | 40 |  | 40 | 0 | 0 | 0 | 1
45 | Members Portal | 50 |  | 50 | 0 | 0 | 0 | 1
46 | Contractors Portal | 50 |  | 50 | 0 | 0 | 0 | 1
47 | Education Portal | 55 |  | 55 | 0 | 0 | 0 | 1
48 | Marketplace App | 40 |  | 40 | 0 | 0 | 0 | 1
50 | Manual Polishing | 40 |  | 40 | 0 | 0 | 0 | 1
51 | System Testing | 40 |  | 40 | 0 | 0 | 0 | 1
52 | System Rollout | 0 |  | 0 | 1 | 0 | 0 | 0

## Subcritical D1
[13 empty] | Phi = | 1.618
ID | Activity | Total Float | Adjusted Outlier | Adjusted Float | Critical | Red | Yellow | Green | Criticality Risk | 0.47159 | Activity Risk | 0.6641 | Fibonacci Formula | 0.3728
2 | Requirements | 30 |  | 30 | 0 | 0 | 0 | 1
3 | Architecture | 15 |  | 15 | 0 | 0 | 1 | 0 | Critical factor | 4
4 | Project Planning | 15 |  | 15 | 0 | 0 | 1 | 0 | Red Factor | 3 | Average | 0.56785
5 | Management Education | 15 |  | 15 | 0 | 0 | 1 | 0 | Yellow Factor | 2
7 | UX Design | 115 | 68 | 68 | 0 | 0 | 0 | 1 | Green Factor | 1
8 | Dev Training | 15 |  | 15 | 0 | 0 | 1 | 0 |  |  | Culling Factor | 1
9 | Test Plan | 150 | 68 | 68 | 0 | 0 | 0 | 1 | Total | 10
10 | Test Harness | 150 | 68 | 68 | 0 | 0 | 0 | 1
11 | Build and Setup | 30 |  | 30 | 0 | 0 | 0 | 1
12 | UI Design | 115 | 68 | 68 | 0 | 0 | 0 | 1 | Red Limit | 9
13 | Manual | 140 | 68 | 68 | 0 | 0 | 0 | 1 | Yellow Limit | 26
14 | Logging | 25 |  | 25 | 0 | 0 | 1 | 0
15 | Message Bus | 20 |  | 20 | 0 | 0 | 1 | 0
16 | Security | 15 |  | 15 | 0 | 0 | 1 | 0
18 | Payments DB | 15 |  | 15 | 0 | 0 | 1 | 0
19 | Members DB | 15 |  | 15 | 0 | 0 | 1 | 0 | Sanity Check: | Passed
20 | Projects DB | 15 |  | 15 | 0 | 0 | 1 | 0
21 | Contractors DB | 15 |  | 15 | 0 | 0 | 1 | 0
22 | Education DB | 15 |  | 15 | 0 | 0 | 1 | 0 | Decompressed by 4 weeks to finish 12/25/15
23 | Workflows Repository | 15 |  | 15 | 0 | 0 | 1 | 0
24 | Regulations DB | 15 |  | 15 | 0 | 0 | 1 | 0
26 | Data Migration | 25 |  | 25 | 0 | 0 | 1 | 0
27 | Payments Access | 25 |  | 25 | 0 | 0 | 1 | 0
28 | Members Access | 15 |  | 15 | 0 | 0 | 1 | 0
29 | Projects Access | 15 |  | 15 | 0 | 0 | 1 | 0
30 | Contractors Access | 25 |  | 25 | 0 | 0 | 1 | 0
31 | Education Access | 15 |  | 15 | 0 | 0 | 1 | 0
32 | Workflows Access | 15 |  | 15 | 0 | 0 | 1 | 0
33 | Regulations Access | 25 |  | 25 | 0 | 0 | 1 | 0
35 | Regulations Engine A | 15 |  | 15 | 0 | 0 | 1 | 0
36 | Regulations Engine B | 15 |  | 15 | 0 | 0 | 1 | 0
37 | Search Engine | 15 |  | 15 | 0 | 0 | 1 | 0
39 | Abstract Manager | 15 |  | 15 | 0 | 0 | 1 | 0
40 | Membership Manager | 15 |  | 15 | 0 | 0 | 1 | 0
41 | Market Manager | 15 |  | 15 | 0 | 0 | 1 | 0
42 | Education Manager | 15 |  | 15 | 0 | 0 | 1 | 0
43 | Regression Test Harness | 15 |  | 15 | 0 | 0 | 1 | 0
45 | Members Portal | 20 |  | 20 | 0 | 0 | 1 | 0
46 | Contractors Portal | 20 |  | 20 | 0 | 0 | 1 | 0
47 | Education Portal | 15 |  | 15 | 0 | 0 | 1 | 0
48 | Marketplace App | 15 |  | 15 | 0 | 0 | 1 | 0
50 | Manual Polishing | 15 |  | 15 | 0 | 0 | 1 | 0
51 | System Testing | 15 |  | 15 | 0 | 0 | 1 | 0
52 | System Rollout | 0 |  | 0 | 1 | 0 | 0 | 0